Step-by-step outline: organising a safe public event for a chalk stream community group

## 1) Define the purpose of the event

Start by being clear about:

- What the event is for – e.g. awareness raising, volunteer recruitment, fundraising, consultation, training, or community action.

- Type of event – public meeting, fundraiser, talk, guided workshop, drop-in session.

- Who it is for – local residents, landowners, schools, partner organisations, families, volunteers.

- Expected numbers – minimum and maximum attendance.

- What success looks like – e.g. 30 attendees, £500 raised, 10 new volunteers, community feedback gathered.

## 2) Choose the location and check permissions

For any public space or public building:

- Confirm who owns or manages the venue/land.

- Ask whether you need: permission to use the space; a booking agreement; public liability insurance; a licence (for alcohol sales, entertainment, street collections, or amplified sound)

## 3) Set the date, time, and format

Choose a date and format that suits your audience:

- Avoid clashes with local major events.

- Consider daylight, weather, parking, and public transport. Build in time for: set-up; arrival and sign-in; the main session; breaks; clear-down

- For a workshop or fundraiser, decide whether people need to book in advance.

## 4) Appoint a small organising team

Even a small event should have named roles:

- Event lead – overall responsibility

- Venue/space coordinator – room layout, access, facilities

- Safety lead – risk assessment, first aid, emergency plan

- Volunteer/steward lead – briefing and roles

- Finance lead – donations, tickets, float, receipts

- Speaker/activity lead – agenda or workshop delivery

- Safeguarding contact – especially if children or vulnerable adults may attend

For smaller events, two or three capable people may be enough if roles are clear.

## 5) Prepare a simple event plan

Write a short plan covering:

- event name, date, time, location

- purpose and audience

- expected attendance

- key contacts and roles

- schedule for the day

- layout or site plan

- safety arrangements

- emergency arrangements

- accessibility arrangements

- communications plan

- clean-up and close-down plan

## 6) Carry out a risk assessment

This is one of the most important steps. Think through what could go wrong and how you will reduce the risk. Typical hazards for a community meeting, fundraiser, or workshop include:

- slips, trips, uneven ground, wet floors, cables

- overcrowding or blocked exits

- severe weather if outdoors

- fire risks

- electrical equipment

- manual handling when moving tables, chairs, displays

- lone working or poor supervision

- cash handling at fundraisers

- food safety if serving refreshments

- safeguarding concerns

- traffic near the venue

- accessibility barriers

- public disorder or conflict

- water hazards if near a river or stream

A good risk assessment should say:

- the hazard

- who may be harmed

- what controls you will use

- who is responsible

- when it will be checked/reviewed

## 7) Plan how to organise the room or public space

Set up the room or space so it is easy to use and safe.

Room/space layout

- Keep entrances, exits, and fire exits clear at all times.

- Leave clear walking routes for all attendees, including wheelchair users.

- Avoid trailing cables or tape them down safely.

- Place sign-in, information, and donation tables where they do not block circulation.

- If you have displays, make sure they are secure and not top-heavy.

- If using chairs: space them sensibly; avoid overcrowding; leave aisles clear

- If outdoors: mark boundaries clearly; think about shelter, shade, and wind; keep any equipment stable and weighted if needed

Suggested layouts

- Community meeting: rows or semi-circle facing speakers, plus sign-in desk and refreshments area

- Workshop: cabaret or small group tables, clear demonstration area, materials station

- Fundraiser: welcome desk, activity zone, raffle/donation point, refreshments, seating area, quiet space

## 8) Organise the people

Think about who is doing what, not just the venue.

Before the event

- Confirm volunteers and speakers.

- Send clear joining instructions: time; location; parking/public transport; accessibility information; what to bring;

- Brief volunteers on: their role; who the event lead is; emergency procedures; how to report concerns

During the event

Have people assigned to: welcome and sign-in / direct attendees / manage the room / support speakers/workshop leads / monitor exits and circulation / handle donations/cash / respond to minor issues / contact emergency services if needed.

After the event

Assign people to: tidy and clear the room; collect equipment; remove waste; close the event safely; record any incidents or lessons learned.

## 9) Put basic safety measures in place

Your arrangements should match the size and nature of the event.

Essentials

- Have a named person in charge on the day.

- Know the maximum capacity of the space.

- Keep exits and access routes clear.

- Know where the nearest toilets, handwashing points, and drinking water are.

- Have a charged phone for emergencies.

- Keep a simple list of emergency contacts.

- Make sure volunteers know how to escalate a problem.

First aid

- Consider whether you need a trained first aider on site.

- Have at least a basic first aid kit available.

- Know the venue address/postcode in case emergency services are needed.

- For larger or more active events, strengthen medical arrangements.

## 10) Fire safety and emergency planning

Even a small event should have a simple emergency plan.

Fire safety

- Identify all exits and assembly points.

- Do not block fire doors or escape routes.

- Check whether the venue has fire extinguishers and alarms.

- Avoid overloading sockets or unsafe electrical setups.

- If using candles, heaters, catering kit, or generators, assess those risks carefully.

Emergency plan

Decide in advance:

- who calls 999

- who meets emergency services

- how attendees will be told to leave

- where people will gather

- how you will account for volunteers

- what happens if a speaker fails to arrive, weather changes, or the venue becomes unsafe

## 11) Plan for safeguarding and inclusion

This matters especially for community groups.

Safeguarding

If children, young people, or vulnerable adults may attend:

- decide whether children must be accompanied

- identify a safeguarding lead

- make sure volunteers know what to do if a concern is raised

- avoid situations where one adult is alone with a child

- assess public-space risks such as toilets, car parks, and open access

The NSPCC Child Protection in Sport Unit highlights the value of a safeguarding-aware risk assessment for activities in public spaces.

Inclusion and accessibility

- Choose an accessible venue where possible

- Consider hearing, mobility, visual, and neurodiverse needs

- Provide seating and a quieter area if possible

- Make signage and instructions clear

- Offer step-free access where available

## 12) Manage food, drink, and fundraising safely

If serving refreshments:

- keep food simple and low risk where possible

- be clear about allergens. Display information from any packets

- maintain hygiene

- make sure hot drinks are managed carefully

If raising money:

- decide whether it will be donations, tickets, raffle, or sales

- check if you need any fundraising or collection permissions

- use two people for counting cash if possible

- keep money secure and out of sight

- record what was taken

## 13) Communicate clearly with attendees

Before the event, tell people:

- what the event is

- when and where it is

- whether they need to book

- who it is for

- accessibility details

- safety information if relevant

- transport and parking advice

- what to do in bad weather if outdoors

## 14) Do a final pre-event check

On the day, do a short walk-through with everyone and clarify any roles and responsibilities.